## Slide 1: Project Management
For ESM 401
20 January 2005

## Slide 2: Overview
Overview of Project Management
Owner’s viewpoint
Public and Government’s viewpoint

## Slide 3: What is a project?
One-of-kind undertaking
Definite objective
Start and end points

## Slide 4: Characteristics
Temporary
Use scarce resources
Specific objectives
Unique outcomes
Special budget
One person has responsibility

## Slide 5: Project Life Cycle

## Slide 6: Organizations
Table of Organization
Regiment
Battalion
Battalion
Battalion
Co.A
Co.C
Co.B
Co.A
Co.C
Co.B
Pl.1
Pl.2
Pl.3
Pl.1
Pl.2
Pl.3

## Slide 7
Functional Organization
  Group by discipline or function
  Line vs. Staff
Colonel
Construction
Design
Permits
Staff B
Staff A

## Slide 8: Functional
http://www.miamidade.gov/wasd/about_table_org.asp

## Slide 9: Staff Functions
(Corps of Engineers, Alaska)
Alaska District Corps of Engineers - Organization Chart

## Slide 10: Organizations
Product
CEO Boeing
747 Jets
757 Jets
Small Planes

## Slide 11: Matrix Organization
CEO
Chief Mechanical
Chief Civil and Soils
Chief Electrical
Project 1 Sid
Project 2 Kid
Project 3 Sue
2 ME
2 CE
5 EE
5 ME
0 CE
2 EE
5 ME
5 CE
5 EE

## Slide 12: Projectized Organization
Just matrix with decreased or absent functional heads

## Slide 13: Concepts
Flattened organization
  Antithesis of triangular organization
Self-directed team
  limiting case of flattened organization

## Slide 14: Three aspects of P.M
Schedule
  time
Cost
  budget
Production
  performance, specification

## Slide 15: Bar Chart Schedules
Most common
Simple
(Excel)
Gantt chart

## Slide 16: CPM
Critical Path Method
PERT (Program Evaluation and Review Technique)
  uses statistical methods

## Slide 17: CPM as Management Tool
Delays on critical path delay job
Document delays
Delay on activities with float will not delay job, up to the amount of float
Experiment with different allocations of overtime, “crashing” activities

## Slide 18: Managerial Accounting, WBS
Work Breakdown Structure

## Slide 19: Cost control
Financial accounting
  accurate to penny
  slow, up to three months after the fact
Managerial accounting, cost accounting
  fast, ASAP
  Why?

## Slide 20: Use of Cost Control
Must be timely
Must indicate strong and weak points
Therefore must tie costs to specific activities
(Excel)

## Slide 21: WBS
Cost codes

## Slide 22: Engineering and Construction Contracts

## Slide 23: Engineering Contracts
A/E = Architect/Engineer
Owner
Contractor
A/E

## Slide 24: A/E contract
Sophisticated vs. non-sophisticated
  Many are non-sophisticated
Often lack clear definition at start

## Slide 25: Design Phases
Preliminary
  Planning
  Programming
Design
  10, 35, 75, 95%
  Bid documents
Construction

## Slide 26: Construction Contracts
Traditional
Owner
Contractor
A/E

## Slide 28
Design-build
Owner
Contractor
A/E
A/E
OR

## Slide 30
Construction (Project) Management
Owner
Contractor
A/E
C M

## Slide 33
Turnkey
Fast track
End result

## Slide 34: The Public Contracting Process
Advertise
Receive Proposals
Open Proposals (Bids)
Evaluate and Award
Work
Changes
Completion
Warrantee

## Slide 35: Private Contracting
Not controlled by law, except
  subcontracts or suppliers on public works
Corporate rules
  SEC
  Accounting and Auditing
Biggest difference is that private can select bidders

## Slide 36: “Construction Documents”
Agreement
Drawings
General Conditions
Special Conditions
Technical Specifications
  Reference specifications and technical documents
Hierarchy statement

## Slide 37: Bid Documents
Many formalities for public construction
“Front end” plus Construction Documents
Bid form
Bid bond
Many miscellaneous forms, see ADOT
“Non-responsive” vs. “Informalities”

## Slide 38: ADOT
DOT&PF - Statewide Design & Engineering Services - D&CS - Preconstruction

## Slide 39: Owner’s Viewpoint on Project

## Slide 40: Need, Planning, and Programming
Need
  Project Selection
Project Concept
Planning and Programming
  Size? Timing? Cost?

## Slide 42: Plan for the Plan
As early as possible in the project
Sufficient time and budget must be available to properly plan the project
Often must ask for these resources before very much is definitely known
Consequently, little planning is done
Until the need for the project is great.

## Slide 43
Often the first real planning and programming revels that the project is behind schedule already.
Old Superintendent to young engineer Perkins, about 1970 or so, “We weren’t supposed to be this far behind schedule for months yet.”

## Slide 44: Consequently
First step for a new project is to secure adequate resources for proper planning of the project.
The “project selection process” always requires estimates of funds required for the project.
So we are asking for resources for a project, before it is “selected.”
  Greatest resource need is often people.

## Slide 45: Public vs. Private
Public projects
  Distinction between new construction (“capital project”) and “maintenance” is established by law.
  Capital projects always require approval of a legislative (law making) body
Private projects
  Often requires approval of a board of directors
    large projects always do

## Slide 46: A fourth aspect of project management
Cost
Schedule
Performance
How will project fit into the organization and its strategies.
Notes: <number>
<footer>
<header>
<date/time>
In order to determine this, we must know the organizations strategy. Where is it going and how will it get there.

## Slide 47: Programs
A “program” may have several projects
Program: Improve the Alaska Highway to national highway system standards
Project: Resurface roadway, Mile 480 to Mile 512
Project: Open new gravel source, East of Delta Junction
Project: Reroute Mile 430 to 455

## Slide 48: Within Projects
No standard nomenclature
Tasks
Sub-tasks
Work Orders
Other logical breakdowns
  WBS

## Slide 49: Capital Expenditures
Goods that have lives longer than one year are capital expenditures.
A new building, automobile, computer for example.
The initial cost may not be taken as an expense in the first year, rather the initial cost must be depreciated over the life of the good.
  Projects are almost always capital expenditures

## Slide 50: DD 1391
The basic programming document in the military construction process, the DD 1391.
This one page documents goes to congress and is part of the military appropriations law for that year.

## Slide 51
It is a brief summary of the project, but has the essentials of cost, schedule and performance.
But note the lack of detail
This document will become the “law” under which the project is built.

## Slide 52: Permits

## Slide 54: Permits
Construction in the U.S. is highly regulated
Larger projects often require permits from Federal, State, and Local Agencies.
These permits are specified in the regulations and usually require certain details be provided before work is allowed to proceed.

## Slide 55
They often have stipulations that require work be done in a certain manner, or at a certain time.
Permits often require a fee.
Permits often require a public notice and comment period.

## Slide 56
Both the permitting agency and those who are likely to comment are important stakeholders in the project.

## Slide 57
Some permits are “routine”
Some are not routine
Many delays and problems in major projects are due to “permitting.”

## Slide 58
The Fort Knox Gold Mine required over 300 separate permits.
Need to enumerate the permits early in the project
Often in the concept stage

## Slide 59: Most important
Who in the project is responsible for getting which permit
  Owner
  Designer
  Contractor
Often it is the Owner, but with the Designer’s support.

## Slide 60: Examples
But first: (It is better for your morale if you consider the important purpose that is driving the regulation and permitting process rather than regarding the regulators as “obstructionists that do not want the project built.”)
In the U.S. bribery is uncommon in the permitting process.
Politics is common, but (Perkins opinion) its effects are exaggerated by people who “have not done their homework.”

## Slide 61: Local Government
Planning and zoning
Building Permit
  Often for each trade: general, plumbing, electrical
  Fire protection may be separate
Block roads
Transport heavy, very large or dangerous materials over local roads (State permit will also be required)
Utilities
  Temporary and Permanent

## Slide 62: State Environmental
Wastewater and water (out-of-town projects)
Air quality for boilers and generators (both temporary and permanent)
Waste disposal plan
Oil pollution control
Stormwater control
http://www.state.ak.us/local/akpages/ENV.CONSERV/permits.htm
http://info.dec.state.ak.us/sps/document.asp

## Slide 63: State Lands Department
Permit to cross state lands
Temporary roads
Permanent, need “right of way”
Cut timber or clear land
Burn wood
Materials mining (gravel)

## Slide 64: State Fish and Game
General permit
Permit to cross streams
Permit for permanent culverts and bridges

## Slide 65: State Labor
Blasting
Elevators

## Slide 66: State Health
Radiation

## Slide 67: State Transportation
Large or Heavy Loads
(Breakup restrictions)

## Slide 68: Federal Lands
Access, Right of Way, etc. on Federal Lands
Minerals, including gravel and soil, for construction

## Slide 69: Federal Environmental
Some are same as state
Dredge spoil

## Slide 70: Environmental Assessments
NEPA, National Environmental Policy Act
NEPA's basic policy is to assure that all branches of government give proper consideration to the environment prior to undertaking any major federal action that significantly affects the environment
Must screen all actions

## Slide 71: Screening Process
Is the action excluded by the law?
  a few are
Next determine the significance to the environment
  “little handle” concept

## Slide 73: Corps of Engineers
Any change to “navigable” river
  dock, bridge
Dredging
Work in “wetlands”

## Slide 74: Federal Aviation
Structures over a certain height
Near airports

## Slide 75: Federal Communications
Temporary radio

## Slide 76: Take home message
All these take TIME.
Often resources
  initial designs
  data, number of people in a construction camp
  schedule
    When the fish are migrating?

## Slide 77: Planning
Acquisition of the proper permits must be accounted for in the project plan.
Often a task for each permit should be in the CPM

## Slide 78: Changes
Get permit for 200 man camp.
Later it must be enlarged to a 250 man camp.
Now need to review ALL the permits
  Which ones need to be modified
  If this is a major modification, you may have to go through the entire public review process.

## Slide 79: Is this may “cutting red tape” or cutting the ribbon at the opening of his project?

## Slide 80: Codes and Standards

## Slide 81
Codes
Standards
Specifications

## Slide 82: Codes
Codes are the law.
Written by a professional organization
Adopted by a government
Government will often add modifications to code.
  To suit local conditions

## Slide 83: Design Review
Code will often specify review of design by local official.

## Slide 84
Most code provision call for “at least” something
You are free to do more
Most codes are conservative
  protective of life and safety
But this not always true

## Slide 85
http://www.dps.state.ak.us/Fire/asp/

## Slide 86: Standards
Recommendations by a professional group
Often adopted by government
Or “referenced” in code.
Which makes them the law as well.

## Slide 87: Standards Setting Bodies
ASTM
ASME
ACGIH
NFPA
AASHTO
API

## Slide 88: ASTM/ASME
American Society of Testing and Materials
http://www.astm.org
American Society of Mechanical Engineers
http://www.asme.org
Ethical problems, resolved

## Slide 89
If the standard is relevant, it is a minimum requirement.

## Slide 90: Problems
So many standards, that are changing all the time
Hard to keep up

## Slide 91: Project
Owner might set minimum standards for the project
Cite for designer
“All welding and radiography on the project will meet API standards.”
Or cite international standards
  often use U.S.

## Slide 92: Specifications
Standard Specs
  CSI
  http://www.csinet.org/about.htm
  http://www.csinet.org/s_csi/docs/9400/9361.pdf
  Corps of Engineers
  http://www.ccb.org/docs/ufgshome/UFGSToc.htm

## Slide 93: Project
Project owner may require a standard specification format, that all designers must use.

## Slide 94: Problems
Conflicts: One contractual document seem to contradict another.
Paradox: The more definite you are, the more voluminous the specifications, the greater the chance of a conflict.
Plans with specifications
Specifications with each other
Specifications with its referenced standards

## Slide 95: Conflicts
Conflicts may result in changes
Public construction, contractor must bid in the least burdensome interpretation.
Will always want more money if there is a change.

## Slide 96: Resolution
Precedence clause of contract may help
Most contracts have such a clause.

## Slide 97: Project Specifications
Large projects will often adopt standard specifications for the project.
Project Style Guide
  English, report forms
  aboveground
  above-ground
  above ground

## Slide 98: Take Home Message
Give attention early to codes and standards for the project.
Cite them in contracts
Standard Specifications can improve communications and reduce errors, if used properly

## Slide 99: Projects and Stakeholders

## Slide 100: Key Concept
“You must accept as fact that you must manage the project from an overall perspective of all the stakeholders – not just the customers and the organization.
“Manage” does not mean you can or should do everything all of the stakeholders desire, but you must consider their desires.

## Slide 101: Who are stakeholders?
Anyone who is interested in project and especially,
Anyone who can harm a project
Organize for explanation, but there is no real organization, it is chaos.

## Slide 102: Primary Stakeholders
Have legal or contractual obligations to the project team.
  Users
  Suppliers, Subcontractors
  Unions
  Shareholders
  Creditors
  Employees
  Government Agencies
Notes: <number>
<footer>
<header>
<date/time>
Examples: project team, shareholders, unions, agiencies, suppliers, customers

## Slide 103: Secondary Stakeholders
Have strong interest in project,
But not legal tie
  Public
  Competitors
  Tourists
  Media
  Families of primary
  Local community
Notes: <number>
<footer>
<header>
<date/time>
Private citizens, consumer groups, environmental groups, “watchdog” groups, anyone who believes they will be affected by the project.

## Slide 104
Relations and communications with stakeholders must be appropriate
Not all are the same
Expectations

## Slide 105: Steps
Identify Stakeholders
Understand their interest
Measure their interest
Predict reaction
Identify effect of reaction on project

## Slide 106: Outline
Meet the Stakeholders so they learn your face
  Leave contact information, get theirs
Seek out contentious issue
  They will arise sooner or later
  Don’t get surprised
Use caution in defining scope, budget timing
Never promise what you cannot (personally) deliver